## BOARD OF TECHNICAL EDUCATION

PORVORIM-GOA

April, 2017 Examinations

Programme: Civil Engg./CT

Subject: Construction Management(CE502)/(5008) [Old/Rev]

# Time Duration: 3 Hrs.                                               Max. Marks: 75

Instructions: 1) All Questions are compulsory.

2) Figures to the right indicate full marks.

3) Assume suitable additional data if required.

| Q.No.1. | Answer the following Questions: | 5 x 3 = 15 |
| --- | --- | --- |
| a) | Define motivation and its importance in construction management. |  |
| b) | Draw neatly sketch of site layout. |  |
| c) | Write the importance and necessity of co-ordinating and controlling. |  |
| d) | What is Inventory control and Store management? |  |
| e) | Write the importance and contents of first aid kit. |  |
| Q.No.2. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | State the types of leadership and explain any one in detail. |  |
| b) | State the objectives and provisions of any two of the following: - Contract Labour Act 1970 - Employee Provident Fund Act 1952 - Workmen’s Compensation Act, 1923 |  |
| c) | State two main stages of planning. Explain one stage in detail. |  |
| Q.No.3. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | Draw a neat organizational chart of line and staff organization and mention its merits and demerits. |  |
| b) | Briefly explain the following types of contracting firms and state their merits and demerits: - Private limited company ii) Partnership firm |  |
| c) | Briefly explain updating of network and rescheduling of resource. |  |
| Q.No.4. | Answer the following Questions: |  |
| a) | What is Bar Chart? What are its limitations? What is PERT? | (4) |
|  | ### OR |  |
| a) | Write a note on “Occupational hazards in construction industry”. | (4) |
| b) | Construct a neat network and find out the critical path of the project, total project duration, EST, EFF and total float. Activity; Duration in week. 1-2; 3. 2-3; 4. 2-4; 6. 3-5; 8. 3-7; 7. 4-5; 4. 4-6; 5. 5-7; 9. 6-7; 6. 7-8; 8. | (8) |
|  |  | …..2/- |
|  | -2- |  |
| Q.No.5. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | Explain briefly the inspection and supervision techniques to be adopted in respect of following works: - Earthwork ii) Water Proofing |  |
| b) | Explain the role of supervisor on construction site. |  |
| c) | Write down the safety measures taken during demolition. |  |
| Q.No.6. | Write short notes on any three: | 3 x 4 = 12 |
| a) | Principle of management |  |
| b) | Duties and responsibilities of builder |  |
| c) | Sole proprietorship |  |
| d) | ISO-9000 series |  |
| e) | Precaution to be taken to avoid accidents on construction site |  |
| f) | Types of communication (only for students of old scheme) |  |

***********