## BOARD OF TECHNICAL EDUCATION

PORVORIM-GOA

April, 2014 Examinations

Programme: Civil Engineering/CT

Subject: Construction Management(5008)

# Time Duration: 3 Hrs.                                               Max. Marks:  75

Instructions: 1) All Questions are compulsory.

2) Figures to the right indicate full marks.

3) Assume suitable additional data if required.

| Q.No.1. | Answer any five of the following Questions: | 5 x 3 = 15 |
| --- | --- | --- |
| a) | List down any six important Laws/Acts related to construction activity. |  |
| b) | What is scientific management? Explain briefly. |  |
| c) | Explain how principles of management are helpful in construction management. |  |
| d) | Briefly explain why communication gains importance in management. |  |
| e) | Explain the role of supervisor/engineer in execution work using different types of drawings on site. |  |
| f) | State the features of Contract Labour Act 1970. |  |
| g) | State any three agencies associated with construction industry and their function. |  |
| Q.No.2. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | State types of organisations. Briefly explain line and staff organisation. |  |
| b) | Explain the organisation structure adopted for private organisations. |  |
| c) | Briefly explain the work involved at pretender and post tender stages. |  |
| Q.No.3. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | Discuss the importance of quality control on construction sites. |  |
| b) | Briefly explain the inspection and supervision techniques adopted for i) Stone masonry ii) Steel work. |  |
| c) | Explain supervision and quality control techniques required during construction work as regards equipments and materials. |  |
| Q.No.4. | Answer any two of the following Questions: |  |
| a) | Briefly explain the fields of applications of PERT. | (4) |
|  | OR |  |
| a) | Define the terms: i)Total float ii)Critical path iii)EST iv)EFT. | (4) |
| b) | Construct the network, mark critical path and calculate total project duration for the data given below. Also calculate total float, EST and EFT for each activity. Activity; Preceeding activity; Duration in days. A; -; 8. B; -; 7. C; -; 13. D; A; 09. E(Dummy); B; 00. F; B; 05. G(Dummy); C; 00. H; C; 08. I; H; 10. J; D, E; 15. K; F, J; 18. | (8) …..2/- |

-2-

| Q.No.5. | Answer any two of the following Questions: | 2 x 6 = 12 |
| --- | --- | --- |
| a) | Write a brief note on occupational hazards in construction industry. |  |
| b) | Discuss the different safety measures adopted during demolition work. |  |
| c) | Bring out salient features of Employees Provident Fund Act 1952. |  |
| Q.No.6. | Write short note on any three: | 3 x 4 = 12 |
| a) | Democratic requirements of an ideal leader |  |
| b) | Types of communications |  |
| c) | Role of construction industry in national development |  |
| d) | Controlling and decision making |  |
| e) | Updating of network |  |

***********