## BOARD OF TECHNICAL EDUCATION

PORVORIM-GOA

November, 2013 Examinations

Programme: Civil Engg./CT

Subject: Construction Management(5008)

# Time Duration: 3 Hrs.                                               Max. Marks:  75

Instructions: 1) All Questions are compulsory.

2) Figures to the right indicate full marks.

3) Assume suitable additional data if required.

| Q.No.1. | Answer any five of the following Questions: | 5 x 3 = 15 |
| --- | --- | --- |
| a) | Bring out the salient features of Employee State Insurance Act 1948. |  |
| b) | State the precautions to be taken during construction activities to prevent the accidents on sites. |  |
| c) | Briefly discuss the functions of management. |  |
| d) | What is motivation? State its functions in management. |  |
| e) | Explain briefly the requirements for equipment management. |  |
| f) | Bring out the importance of human resource management in construction industry. |  |
| g) | State the important features of functional organisation. |  |
| Q.No.2. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | Explain the organisation structure of construction corporations. |  |
| b) | State the different types of contracting firms and briefly explain any two of them. |  |
| c) | Bring out the importance of site layout in proper and timely execution of construction works. |  |
| Q.No.3. | Answer any two of the following Questions: | 2 x 6 = 12 |
| a) | Explain the inspection and supervision techniques employed for (i) Woodwork and (ii) form work. |  |
| b) | Briefly explain the sampling techniques for testing of materials. |  |
| c) | What are specifications? Explain briefly the principles adopted for inspection and enforcement of specifications. |  |
| Q.No.4. | Answer the following Questions: |  |
| a) | What is PERT? What are its advantages over CPM? | (4) |
|  | ### OR |  |
| a) | Bring out the advantage of network analysis in construction project management. | (4) |
| b) | For the following data about activities, construct a network and locate the critical path. Also calculate total project duration and total float, EST, EFT for ach activity. | (8) |
| Activity; 1-2; 1-3; 1-4; 2-4; 3-4; 3-5; 4-7; 4-5; 5-6; 4-6; 7-6. Duration in weeks; 04; 06; 14; 08; 10; 07; 05; 06; 04; 07; 09. |

………2/-

-2-

| Q.No.5. | Answer any two of the following Questions: | 2 x 6 = 12 |
| --- | --- | --- |
| a) | Write a brief note on Personal management in construction industry. |  |
| b) | List down the safety measures taken during fabrication and erection works and explain briefly. |  |
| c) | Bring out the salient features of Trade Union Act 1926. |  |
| Q.No.6. | Write short notes on any three: | 3 x 4 = 12 |
| a) | Authoritarian requirements of ideal leader |  |
| b) | Principles of management |  |
| c) | Necessity and importance of planning |  |
| d) | Rescheduling of resources |  |
| e) | Importance of safety in construction |  |

***********